## Sheet2
Format for Technical Pre-Bid Queries
Tender No | TPNODL/OT/2021-22/064
Package Name | Rate Contract for WIFI Devices
Note : | The said format to be used only for any Pre-bid Query / Clarifiaction/ Deviation on any of the Tender documents
Sr. No. | Detailed Reference to concerned Document . Please specify Document No / Clause No / Page No | Description as per Bid Document | Query / Clarification / Deviation |  | TPNODL Response
1 | 2 | 3 | 4 | 5
1 | TPNODL/OT/2021-22/064/Annexure II/Technical Specification/Wireless Controller/Point 2-G/Page No. 18 | Controller should support minimum 1000 WLAN’s. | Kindly elaborate on the design of the network with the requirement of 1000 WLANs |  | Wifi devices will be installed at different office locations that to be controlled by one controller
2 | TPNODL/OT/2021-22/064/Annexure II/Technical Specification/Wireless Controller/Point 4-K/Page No. 20 | WLC or integrated solution should provide customised reporting with minimum 15 days of historical WLAN information. | Histortical WLAN information is a deliverable of an NMS solution. To ensure high-quality performance, WLC reflects real time data and is connected to an NMS solution for history. |  | Design to be provided by the bidder before bid finalization
3 | TPNODL/OT/2021-22/064/Annexure II/Technical Specification/Wireless Access Point/Point 17/Page No. 21 | Should support 500 or more clients per AP. | Kindly elaborate on the use case. Essentially to support good performance, 400 clients per AP is a recommended number from the industry. |  | RFP stands final
4 | TPNODL/OT/2021-22/064/Annexure II/Technical Specification/Wireless Access Point/Point 19/Page No. 21 | The Access Point should support mesh configuration either directly or through the controller. | Kindly elaborate on the use case of supporting Mesh configuration in an indoor Access Point. In case an external access point is required, kindly alter the requirement as menetioned in the RFP. |  | Wifi devices will be installed at different office locations that to be controlled by one controller and no external AP is required
5 | TPNODL/OT/2021-22/064/Annexure II/Technical Specification/Wireless Access Point/Point 21/Page No. 22 | Operating Temperature: 0ºC (32ºF) - 50ºC (122ºF). Operating Humidity: up to 95% non-condensing. | Kindly elaborate on the Operating humidity requirement as with the given weather conditions, in a non-condensing environment, 90% humidity is reached at maximum. |  | Ok
6 | TPNODL/OT/2021-22/064/Point 7- Post Award Contract Administration /Point 7.3- Delivery Terms/Page No. 14 | The material shall be delivered within 6 weeks from issue of release order against the Rate contract. | Amend Delivery Time to 8-10 weeks as because of Covid delivery is getting impacted. |  | RFP stands final
7 | General Queries | Annexure I/Point 1/ Supply of Wireless Access Points as per the spec. with 7 years warranty Annexure I/Point 2/Supply of Wireless Controller as per spec with 7 years Warranty Annexure II/Technical Specification/Wireless Controller/Point 8-A/Warranty/The WLAN Controller should be quoted with TAC Support and Warranty for 5 years with NBD Hardware Replacement. Annexure II/Technical Specification/Wireless Access Point/Point 25/The Access Point should be quoted with TAC Support and Warranty for 5 years with NBD Hardware Replacement. | Please Clarify whether we will go for 7 years or 5 years warranty. |  | Strictly 7 years warranty as mentioned in Schedule of Items
8 |  | The bidder should have executed similar works for Cumlative Rs.2 Cr. During last 3 years. | The bidder should have executed similar works for Cumlative Rs.2 Cr. During last 5 years. | Since Normal warranty covers under 5 years contract in Wifi Devices . This can be for larger participation. | Your Query is Not Clear
Delivery Terms
9 |  | The Material Shall be Delivered within 6 weeks from issue of release order against the Rate Contract. | The device will be dilvered with in 12-14 weeks after receiving PO & we need 2 weeks for Installation from the date of intimation. | Due to global Pandemic , delay in delivery Globally | RFP stands final
MSME
10 | New Clause Request |  | As per Govt. Guideline all MSME Vendors are eligible for 50% on EMD or Waiver. And In TPDDL, TPSODL & TPWODL we have been entrusted with zero Tender Fee as well 50% of EMD Amount. |  | Please refer our GCC, wherein clause MSME is mentioned.
SLA
11 |  | SLA not Available in Tender Document. | Kindly share the SLA Details. |  | Already mentioned in RFP
13 | 14 | 7.3 Delivery Terms | The material shall be delivered within 6 weeks from issue of release order against the Rate contract. | Due to global semiconductor soratge ,all major OEMs delivery is getting delayed these days( 16 Weeks) . Delivery timeline should be 18 weeks including instalaltion , | RFP stands final
14 | 16 | Schedule of items | Different location sites for supply, installation, testing and commissioning will be shared by TPNODL with the successful bidder. | Request TPNODL to define number of location and APs per location. Which will help us to factor Exact installation and Manpower | Multiple offices scattered among 5 districts i.e. Balasore, Mayurbhaj, Jajpur, Keonjhar & Bhadrak
15 | 16 | 15.0 LIQUIDATED DAMAGES | Liquidated damages @1% of the total executed contract value per week or part thereof, for the period of delay in integrated completion, subject to maximum 10% of the value of the contract shall | Request to change to " Liquidated damages @0.5% of the total executed contract value per week or part thereof, for the period of delay in integrated completion, subject to maximum 5% of the value of the contract." This is required as delivery from all leading OEM is getting delayed | Not Accepatable
16 | 18 | Technical Specifications For Wireless Controller | Controller should support 100 AP from day one and should be scalable upto 2000 APs in a clustered configuration. Each WLC (primary and Redundant) should be able to support minimum 1024 campus connected AP’s or more with support of seamless roaming access over L2/L3 network. | Please consider clustering of WLCs and distributed design deployment wherein multiple instances can be managed from one single dashboard giving seamless perfomance. | RFP stands final
17 | 18 | Technical Specifications For Wireless Controller | Controller should support minimum 1000 WLAN’s. | Kindly elaborate on the design of the network with the requirement of 1000 WLANs. | Wifi devices will be installed at different office locations that to be controlled by one controller
18 | 19 | Technical Specifications For Wireless Controller | Auto Deployment of AP's at different locations | Need complete address of all locations with nos of AP quantity required to deploy at each location. Customer need to share building layout | Multiple offices scattered among 5 districts i.e. Balasore, Mayurbhaj, Jajpur, Keonjhar & Bhadrak. Exact locations will be shared with the successful bidder
19 | 20 | Technical Specifications For Wireless Controller | WLC or integrated solution should provide customised reporting with minimum 15 days of historical WLAN information. | Histortical WLAN information is a deliverable of an NMS solution. To ensure high-quality performance, WLC reflects real time data and is connected to an NMS solution for history. Request to change to 7 days | RFP stands final
20 | 21 | Technical Specifications For Wireless Acces Points | Should support 500 or more clients per AP. | Kindly elaborate on the use case. Essentially to support good performance, 400 clients per AP is a recommended number from the industry. Request to reduce to 400 | FP stands final
21 | 21 | Technical Specifications For Wireless Acces Points | The Access Point should support mesh configuration either directly or through the controller. | Kindly elaborate on the use case of supporting Mesh configuration in an indoor Access Point. In case an external access point is required, kindly alter the requirement as menetioned in the RFP. Request to remove this clause | Wifi devices will be installed at different office locations that to be controlled by one controller and no external AP is required
22 | 22 | Technical Specifications For Wireless Acces Points | Operating Temperature: 0ºC (32ºF) - 50ºC (122ºF). Operating Humidity: up to 95% non-condensing. | Kindly elaborate on the Operating humidity requirement as with the given weather conditions, in a non-condensing environment, 90% humidity is reached at maximum. Request to change to 90 % | Ok
23 | 31 | 3. Scope of Work | General | We Asume PoE Switch , Rack and UPS to be provided by the customer. Help to share Make and model of the Switch | all the switch available are non POE switch so PO adapter is required
24 | 39 | 6.0 TERMS OF PAYMENT | 5% of the Release Order/ Purchase Order price shall be paid as initial interest free advance on fulfillment of the following by the Associate: a) Acceptance of PO/ LOI. b) Submission of advance payment BG (APBG) of 15% of the Release Order/ Purchase Order price which shall remain valid till the advance is fully adjusted. c) Submission of Contract Performance Bank Guarantee (CPBG) of 5/10% of the RC/ PO price valid till 30 days after taking over of the works. B. 10% of the Release Order/ Purchase Order price shall be paid as interest free advance against approval of drawings under Category-1 of major drawings, Quality Plans, Pert Chart, Field Quality Plan, posting of Project Manager and commencement of the first mile stone of the work mutually agreed including C-3 Form, and submission of a true copy of ‘Erection All Risk Insurance Policy’ taken for the awarded jobs. The drawing list shall be mutually agreed at the time of award of work. C. 50% on account payment of the total of item wise cost of material Release Order/ Purchase Order shall be paid against receipt of material at site in good condition and certification by TPNODL along with bills complete in all respects viz. MDCCs etc. D. 20% on account payment of the actual executed value shall be paid against mechanical completion of erection on prorate basis against monthly bills and 70% on account of the actual executed value shall be paid against the service line item including composite line item. In case this milestone is not completed beyond 120 days for reasons attributable to TPNODL, the payment corresponding to supply part shall be released subject to submission of BG of equivalent amount by the BA valid for a period of further 12 months. If required, it shall be extended by the BA on request of TPNODL. E. 15% payment of the actual executed Release Order/ Purchase Order shall be paid after completion of acceptance test and Taking Over of the complete systems specified in the enquiry, including clearance of Electrical Inspection, compliance of final punch point and after reconciliation & adjustment of payments, if any, towards Quantities of materials issued from purchaser’s stock and consumed by the contractor for expeditious completion of the job. In case this milestone is not completed beyond 120 days beyond schedule for reasons attributable to TPNODL, the payment corresponding to supply part shall be released subject to submission of BG of equivalent amount by the BA valid for a period of further 12 months. If required, it shall be extended by the BA on request of TPNODL. | Request to make Payment terms as 30% With PO & balance 70% on successful delivery & installation. | Payment Terms: 100% payment shall be made on pro-rata bases after supply and installation, testing & commissioning as per E-I-C instruction. The payment shall be released within 30 days from date of submission of invoice.
25 |  | Technical Specifications For Wireless Controller | Controller should support minimum 1000 WLAN’s | Kindly elaborate on the design of the network with the requirement of 1000 WLANs | Wifi devices will be installed at different office locations that to be controlled by one controller
26 |  | Technical Specifications For Wireless Controller | WLC or integrated solution should provide customised reporting with minimum 15 days of historical WLAN information. | Histortical WLAN information is a deliverable of an NMS solution. To ensure highquality performance, WLC reflects real time data and is connected to an NMS solution for history. | Design to be provided by the bidder before bid finalization
27 |  | Technical Specifications For Wireless Access Point | Should support 500 or more clients per AP | Kindly elaborate on the use case. Essentially to support good performance, 400 clients per AP is a recommended number from the industry. | RFP stands final
28 |  | Technical Specifications For Wireless Access Point | The Access Point should support mesh configuration either directly or through the controller | Kindly elaborate on the use case of supporting Mesh configuration in an indoor Access Point. In case an external access point is required, kindly alter the requirement as mentioned in the RFP. | Wifi devices will be installed at different office locations that to be controlled by one controller and no external AP is required
29 |  | Technical Specifications For Wireless Access Point | Operating Temperature: 0ºC (32ºF) - 50ºC (122ºF). Operating Humidity: up to 95% non-condensing. | Operating Temperature: 0ºC (32ºF) - 50ºC (122ºF). Operating Humidity: up to 95% non-condensing.