## Sheet1
Tender No | TPNODL/OT/2021-22/088 Dtd.08.10.2021
Package Name | RC For Supply And Installation Of AC At Different Office Building, TPNODL Purpose/Necessity-For New Office Infrastructure
Note : | The said format to be used only for any Pre-bid Query / Clarifiaction/ Deviation on any of the Tender documents
Sr. No. | Detailed Reference to concerned Document . Please specify Document No / Clause No / Page No | Description as per Bid Document | Query / Clarification / Deviation | Clarification | TPNODL Response
1 | 2 | 3 | 4 |  | 5
2 | Annexure I /Sl No. 5 / Page No.17 | Supply of Ceiling Mounted Cassette AC including cordless remote 2.3 Tr. | No availability of Ceiling Mounted Cassette AC of 2.3 Tr. | Availability of Ceiling Mounted Cassette AC of 2 Tr. | Go ahead
3 | Annexure I /Sl No. 7 / Page No.17 | Supply of Ceiling Mounted Cassette AC including cordless remote 1 Tr. | No availability of Ceiling Mounted Cassette AC of 1 Tr. | Availability of Ceiling Mounted Cassette AC of 1.5 Tr. | Go ahead
4 | Annexure I /Sl No. 8 / Page No.17 | Supply of Wall Mounted Split Inverter AC including cordless remote 2.3 Tr. | No availability of Wall Mounted Split Inverter AC of 2.3 Tr. | Availability of Wall Mounted Split Inverter AC of 2 Tr. | Go ahead
5 | 7.2(Page no-14) | 100% payment shall be made to BA within 30 days on receipt of Bills subject to successful delivery & installation | 80%age of the contract value may be paid after successful delivery of materials at concerned site before installation. |  | Ok. 80% payment shall be made against supply of material in good condition at TPNODL- site/ store. Balance 20% payment shall made post sucessful installation. In case TPNODL will not give the site clearance for installation of ACs within 3 months from date of delivery of material, hence; balance 20% payment against supply part shall be cleared by TPNODL. However, amount towards installation shall be be made after sucessful installation & commissioniung of work. Note- All invoices shall be duly verified by user group (E-I-C).
6 | 7.3(Page no-14) | Material should be delivered within 21 days of placement of Release Order (RO). RO shall be placed against the awarded Rate Contract by TPNODL as per requirements arise | RO against certain quantity of materials may be specified else the BA may face problem to supply a bulk quantity of Items at once within such less time. | 30 quantity against RO can be taken at each Lot for smooth execution of work and site execution | 30 quantity against RO can be taken at each Lot for smooth execution of work and site execution
7 | Annexure I Schedule of Items Sl no-11 | Supplying, Installing, Testing and Commissioning of 5kVA Stabilizer | Is there any particular Specification/approved make to be considered by us. | Input Power - 130 to 300, Out Power - 220 to 250, Display - LED,Protection – Under Volt & Over Volt Protection, Mount Type - Wall, Coil – Copper Winding, Cabinet Material - ABS, Phase - Single, Warranty - 3 years BRAND (V-Guard, Luminous, Microtex) | Input Power - 130 to 300, Out Power - 220 to 250, Display - LED,Protection – Under Volt & Over Volt Protection, Mount Type - Wall, Coil – Copper Winding, Cabinet Material - ABS, Phase - Single, Warranty - 3 years BRAND (V-Guard, Luminous, Microtex)
8 | Annexure I Schedule of Items Sl no-12 | Supplying, Installing, Testing and Commissioning of 4kVA Stabilizer | Is there any particular Specification/approved make to be considered by us. | Input Power - 130 to 300, Out Power - 220 to 250, Display - LED,Protection – Under Volt & Over Volt Protection, Mount Type - Wall, Coil – Copper Winding, Cabinet Material - ABS, Phase - Single, Warranty - 3 years BRAND (V-Guard, Luminous, Microtex) | Input Power - 130 to 300, Out Power - 220 to 250, Display - LED,Protection – Under Volt & Over Volt Protection, Mount Type - Wall, Coil – Copper Winding, Cabinet Material - ABS, Phase - Single, Warranty - 3 years BRAND (V-Guard, Luminous, Microtex)
9 | 17 | Annexure I, Schedule of Items, Sr. No. 3 | Installation, Testing, and Commissioning of Split ACs | Capacity not mentioned | (2 Tr, 1.5 Tr and 1 Tr)
10 | 17 | Annexure I, Schedule of Items, Sr. No. 8 | Supply of Wall Mounted Split Inverter AC including cordless remote 2.3 TR | Please clarify that the capacity is 2.3Tr or 2 Tr 3 Star | 2 Tr 3 star
11 | 20 | Annexure III, Commercial Specifications, Sr. No. 7 | Validity of Bid asked as 180days from date of technical opening | We will be able to provide Validity of Bid till 31st Dec 2021 | As per Tender specification